## Instructions
Instructions:
1) Decide your metrics. What is important? How much will the project help new sales? How much will the project help keep existing customers?
2) Make these columns in the spreadsheet. Each of these columns will have a value from 1-5 with 1 being minimal effect, and 5 being a maximum effect. Each of the values will also be weighted by a value in the weights sheet. In this case, a value from 1-5.
3) Categorize the proejcts. Will they help with quality, the architecture, the performance? Is it a project that's visionary or strategic?
4) These categories also become columns in the spreadsheet. Each of these columns will have a "yes" or "no" answer and will be weighted by a value in the weights sheet. Again, in this case, each of these weights will be a value from 1-5.
5) Ask other important questions. Is the project funded? How much will it cost?
6) These columns might have "yes" or "no" values such as the funded column which is not weighted, or they might have a value, as with the "cost' column.
7) In this spreadsheet, we multiply each column by its weight, then we add them together, however the cost column is subtracted since it is a cost rather than a benefit.
8) Rank the final score and make sure that "must" do items are at the top.
9) Adjust the "resources" number in the weights sheet to reflect the proper amount. Then, as long as the units between the values in the spreadsheet and the value of the resources amount are the same, any numbers over the amount of resources should be red and underlined.
10) This tells you where the "red line" is and which projects will be done this cycle, and which are off the table.
11) Use the red-line to figure out which projects are in-scope and which are not.
As with all of my templates, the Project Planning & Scoring Template is licensed under the Creative Commons Attribution-ShareAlike 3.0 Unported License. To view a copy of this license, visit http://creativecommons.org/licenses/by-sa/3.0/.

## Project Scoring
Project | Sales Potential | Sales Weighted | Customer Need | Customer Weighted | Quality | Quality Weighted | Architecture | Architecture Weighted | Performance | Performance Weighted | Vision | Vision Weighted | Strategy | Strategy Weighted | Funded | Cost | Cost Weighted | Running Total Cost | Score
P11 | 5 | 25 | 3 | 6 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 3 | 1 | 5 | 2 | 5 | 32
P8 | 2 | 10 | 4 | 8 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 5 | 10 | 10 | 8
P14 | 4 | 20 | 2 | 4 |  | 0 |  | 0 | 1 | 1 |  | 0 |  | 0 | 1 | 12 | 24 | 22 | 1
P9 | 5 | 25 | 2 | 4 |  | 0 |  | 0 |  | 0 | 1 | 4 |  | 0 |  | 2 | 4 | 24 | 29
P2 | 2 | 10 | 5 | 10 |  | 0 | 1 | 2 |  | 0 | 1 | 4 |  | 0 |  | 2 | 4 | 26 | 22
P4 | 4 | 20 | 2 | 4 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 3 |  | 5 | 10 | 31 | 17
P7 | 4 | 20 | 5 | 10 |  | 0 | 1 | 2 |  | 0 |  | 0 |  | 0 |  | 8 | 16 | 39 | 16
P3 | 5 | 25 | 3 | 6 |  | 0 | 1 | 2 |  | 0 |  | 0 |  | 0 |  | 9 | 18 | 48 | 15
P5 | 3 | 15 | 3 | 6 |  | 0 |  | 0 | 1 | 1 |  | 0 |  | 0 |  | 6 | 12 | 54 | 10
P13 | 1 | 5 | 4 | 8 | 1 | 3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4 | 8 | 58 | 8
P1 | 1 | 5 | 5 | 10 | 1 | 3 |  | 0 | 1 | 1 |  | 0 |  | 0 |  | 6 | 12 | 64 | 7
P6 | 1 | 5 | 2 | 4 | 1 | 3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 3 | 6 | 67 | 6
P12 | 3 | 15 | 2 | 4 |  | 0 |  | 0 |  | 0 | 1 | 4 |  | 0 |  | 11 | 22 | 78 | 1
P10 | 1 | 5 | 3 | 6 |  | 0 |  | 0 |  | 0 | 1 | 4 |  | 0 |  | 9 | 18 | 87 | -3

## Weights
Sales Weight | 5
Customer Weight | 2
Quality Weight | 3
Architecture Weight | 2
Performance Weight | 1
Vision Weight | 4
Strategy Weight | 3
Cost Weight | 2
Resources to allocate | 45